## Risk Register Starter
#VALUE!
Template: Risk Register Starter
A simple way to capture risks from day one.
Doc ID | LS-TEM-0002 | Doc Type | Template
Version | v1.0 | Status | Approved
Confidentiality | Public | Last Updated | 2025-09-27
Principal | Transparancy | Next Review | 2026-06-30
Change Log
Date | Author | Change | Version
2025-09-27 | LucidSeal | Initial Version | v1.0

## Risk Register Guide
#VALUE!
Risk Register Guide
This template is:
🪶 Lightweight - easy to start with, not over-engineered.
✏️ Editable - adapt columns, scoring, and language to suit your organisation.
🛠️ Practical - helps you see risks, owners, and actions clearly.
Purpose
A risk register helps you:
Identify risks early (before they grow).
Track who owns each risk and what’s being done.
Show progress to boards, funders, and your community.
This starter focuses on the essentials:
¦ ID ¦ Description ¦ Impact ¦ Likelihood ¦ Score ¦ Owner ¦ Target Date ¦ Status ¦ Mitigation ¦
How to use
1. Start small - add 3–5 real risks you’re aware of today.
2. Be honest - it’s better to capture an uncomfortable risk than ignore it.
3. Review regularly - update status, dates, and mitigations.
4. Adapt - add or remove columns as your maturity grows.
💡 Tip for community use: Use this as a shared tool in meetings. It helps everyone see risks in plain language, not just as a “compliance exercise.”
Risk Scoring
Risks are scored by multiplying Impact × Likelihood.
This helps prioritise which risks to act on first.
Impact | What it means | Score range (example)
Low (1) | Minor inconvenience, easy to recover. | 1–5
Medium (2–3) | Noticeable impact, requires time or resources to fix. | 6–10
High (4–5) | Serious impact on people, trust, finances, or reputation. | 11–25
Likelihood | What it means
Rare (1) | Very unlikely, but not impossible.
Unlikely (2) | Could happen, but not expected.
Possible (3) | Might happen occasionally.
Likely (4) | Expected to happen at some point.
Almost Certain (5) | Very likely or already happening.
Status Definitions
Status | What it means
Open | Risk is identified but not yet addressed.
Mitigating | Steps are being taken to reduce the risk.
Closed | Risk has been addressed or is no longer relevant.
Tips
Consistency matters - agree on what “High” or “Likely” means for your group.
Keep it living - review the register regularly (e.g., quarterly).
Stay plain - use simple, non-jargon descriptions so everyone understands.
💡 Tip for community use: Encourage different perspectives. Risks spotted by staff, volunteers, and community members may be different - and that’s valuable.

## Risk Register Template
ID | Description | Impact | Likelihood | Score | Owner | Target Date | Status | Mitigation
R-001 | Outdated software not patched. | High | Likely | 12 | Tech Lead | 2025-09-30 | Open | Implement regular patching cycles & notifications
R-002 | Privacy notice unclear. | High | Possible | 9 | Compliance Lead | 2025-09-30 | Mitigating | Use LucidSeal short template, Implement regular document review
R-003 | Stakeholders not heard | Medium | Unlikely | 4 | Engagement Lead | 2025-09-30 | Closed | Feedback form implemnted with quarterly review
|  | High | Unlikely | 6 |  |  | Mitigating
|  | Low | Almost Certain | 5 |  |  | Open
|  | High | Rare | 3 |  |  | Closed